## Embedded_Responses
Timestamp | Task Name | Engineer | Department | Project | Task ID | Description | Start Time | End Time | Status

## Engineer_Credentials
Engineer_ID | Name | Password | Department | Last_Login
eng_seif | Eng. Seif | password123 | Embedded | 2025-10-28 17:02
eng_mohaned | Eng. Mohaned | password123 | Mechanical
eng_maged | Eng. Maged | password123 | AI
eng_rawan | Eng. Rawan | password123 | Visual/Graphic
eng_nehal | Eng. Nehal | password123 | Flutter
assem_murad | Assem Murad | password123 | Mechanical
eng_asem | Eng. Asem Alroomy | password123 | Embedded

## Pending_Projects
Project ID | Project Name | Description | Deadline | Departments | Tasks | Created By | Created At | Status
PROJ_202510300_221242 | bb test | Educational STEM project with modular components | 2025-11-26 | AI | [{"status":"Not Started","name":"Requirements Analysis & Planning","assignedTo":"","id":"BBT-01","description":"Requirements Analysis & Planning for bb test","department":"","deadline":"2025-11-26"},{"department":"","id":"BBT-02","name":"Design & Architecture","status":"Not Started","deadline":"2025-11-26","assignedTo":"","description":"Design & Architecture for bb test"},{"id":"BBT-03","name":"Development & Implementation","assignedTo":"","deadline":"2025-11-26","status":"Not Started","department":"","description":"Development & Implementation for bb test"}] | asemalroomy5@gmail.com | 2025-10-27 22:13 | Pending Review

## TempProjectCreator
ProjectName | ProjectDescription | ProjectDeadline | Departments | Engineers | Notifications | TaskCount | LastUpdated
Generic Kit | Project description | 2025-11-20 | Mechanical,Embedded | Assem Murad,Ahmed Mohsen,Eng. Asem Alroomy | CTO:true,Managers:true,Engineers:true | 3 | 2025-10-22 13:13

## TempProjectTasks
TaskIndex | TaskID | TaskName | Department | AssignedTo | Description | Deadline
1 | GK-001 | Generic Kit - Requirements & Planning | Mechanical | Assem Murad | Define project requirements, scope, and initial planning | 2025-11-20
2 | GK-002 | Generic Kit - Design & Architecture | Mechanical | Assem Murad | Create system architecture and design specifications | 2025-11-20
3 | GK-003 | Generic Kit - Development & Implementation | Mechanical | Ahmed Mohsen | Main development and implementation work | 2025-11-20

## Eng_Mohaned_Team
Timestamp | Date | Engineer | Department | Project | TaskID | Feature/Module | Description | Start Time | End Time | Ref | Status | Notes | Assigner | DurationHours

## Eng_Seif_Team
Timestamp | Date | Engineer | Department | Project | TaskID | Feature/Module | Description | Start Time | End Time | Ref | Status | Notes | Assigner | DurationHours

## Eng_Rawan_Team
Timestamp | Date | Engineer | Department | Project | TaskID | Feature/Module | Description | Start Time | End Time | Ref | Status | Notes | Assigner | DurationHours

## Eng_Nehal_Team
Timestamp | Date | Engineer | Department | Project | TaskID | Feature/Module | Description | Start Time | End Time | Ref | Status | Notes | Assigner | DurationHours

## Eng_Maged_Team
Timestamp | Date | Engineer | Department | Project | TaskID | Feature/Module | Description | Start Time | End Time | Ref | Status | Notes | Assigner | DurationHours
2025-10-21 11:20 | tesr | asemalroomy5@gmail.com | AI | Alf Bot | Custom | test | 0.375 | 0.41667 | Done
2025-10-21 11:20 | b | asemalroomy5@gmail.com | AI | Alf Bot |  | bb | 0.41667 | 0.45833 | Ongoing

## Projects_Tasks
Type | Project ID | Project Name | Department(s) | Status | Manager | Task ID | Task Name | Assigned To | Department | Notes | Deadline
Project | GEN | Generic Kit Phase1 | Mechanical, Visual/Graphic | Active | CTO |  |  |  |  | Educational STEM project with modular components | 2025-11-15
Task | GEN | Generic Kit Phase1 |  |  |  | GEN-01 | Alef Bot Generic Concept | Eng. Rawan | Visual/Graphic | -Slice Alef Bot on SlicerForFusion -Try 2 different sizes to make the descicsion -Export DXFs, Fabricate and Assemble -iterate if needed and finalize -present the models | 2025-10-29
Task | GEN | Generic Kit Phase1 |  |  |  | GEN-02 | Robotic Arm Generic Concept | Haisam | Mechanical | -Review the generic kit models -import needed files -design Robot Arm Links (3DOF) -Design Robot Gripper -Design Servo motor mount | 2025-10-29
Task | GEN | Generic Kit Phase1 |  |  |  | GEN-03 | Generic House Modifications | Ahmed Mohsen | Mechanical | -Reduce size to 150 x 150 x 250 mm -Change single Links in the base to FRAMES | 2025-10-29
Project | SUM | Sumo Car Kit | Visual/Graphic | Active | CTO |  |  |  |  | Educational STEM project for the upcoming Event | 2025-10-30
Task | SUM | Sumo Car Kit |  |  |  | SUM-01 | Designing the figures | Eng. Rawan | Visual/Graphic | Designing the figures for Sumo Car Kit | 2025-10-30
Task | SUM | Sumo Car Kit |  |  |  | SUM-02 | Printing the figures | Eng. Rawan | Visual/Graphic | Printing the figures Sumo Car Kit | 2025-10-30
Task | SUM | Sumo Car Kit |  |  |  | SUM-03 | Printing the figures | Ahmed Mohsen | Mechanical | Printing the figures for Sumo Car Kit | 2025-10-30
Task | SUM | Sumo Car Kit |  |  |  | SUM-04 | add Colors to the figures | Eng. Rawan | Visual/Graphic | add Colors to the figures for Sumo Car Kit | 2025-10-30
Task | SUM | Sumo Car Kit |  |  |  | SUM-05 | add Colors to the figures | Nouran | Visual/Graphic | add Colors to the figures for Sumo Car Kit | 2025-10-30

## Project_List
Project Name | Department(s) | Status | Manager
RC Car | Embedded | Active | Eng. Seif
Hydroponics | Mechanical | Active | Eng. Seif
Generic Kit | Mechanical | Active | Eng. Mohanad
Alf Bot | AI | Active | Eng. Maged
Pyra Brain | Embedded, AI | Active | Eng. Seif
Curriculum Bots Design | Mechanical | Active | Eng. Ahmed Mohsen

## AI_Data_Responses
Timestamp | Task Name | Engineer | Department | Project | Task ID | Description | Start Time | End Time | Status

## Mechanical_Responses
Timestamp | Task Name | Engineer | Department | Project | Task ID | Description | Start Time | End Time | Status
2025-10-27 17:27 | Robotic Arm Generic Concept | haythamkhaledeng@gmail.com | Mechanical | GEN | GEN-02 | -Review the generic kit models -import needed files -design Robot Arm Links (3DOF) -Design Robot Gripper -Design Servo motor mount | 13:00 | 17:00 | Ongoing
2025-10-27 17:27 | 3D printing a clearance palette | haythamkhaledeng@gmail.com | Mechanical | GEN | CUSTOM_1761575110567 | 3D printing a clearance palette | 11:30 | 13:00 | Done
2025-10-28 11:45 | Generic House Modifications | ahmedmohsen4h4@gmail.com | Mechanical | GEN | GEN-03 | -Reduce size to 150 x 150 x 250 mm -Change single Links in the base to FRAMES | 9:00 | 11:00 | Ongoing
2025-10-28 11:45 | Printing the figures | ahmedmohsen4h4@gmail.com | Mechanical | GEN | SUM-03 | Printing the figures for Sumo Car Kit | 11:00 | 13:00 | Ongoing
2025-10-27 | elegoo 3d printer | ahmedmohsen4h4@gmail.com | Mechanical | GEN | CUSTOM_1761640851671 | Performed maintenance on the printer head of the 3D printer. Cleaned and inspected the head to ensure proper resin flow and movement. Removed any cured resin and checked nozzle alignment. Verified smooth operation after reassembly. | 13:00 | 17:00 | Done
2025-10-28 17:09 | Robotic Arm Generic Concept | haythamkhaledeng@gmail.com | Mechanical | GEN | GEN-02 | -Review the generic kit models -import needed files -design Robot Arm Links (3DOF) -Design Robot Gripper -Design Servo motor mount | 9:00 | 17:00 | Ongoing

## VisualGraphic_Responses
Timestamp | Task Name | Engineer | Department | Project | Task ID | Description | Start Time | End Time | Status

## Manager Dashboard
Date | Department | Project | Total Reports | Unique Members | Last Submission | Pending Members
No reports found in the last 7 days.

## Team_Mapping
Senior Name | Junior Name | Department | Email | Role | Level
Eng. Mohaned |  | Mechanical | eng.mohaned@pyramakerz.com | Senior | Senior
Eng. Mohaned | Assem Murad | Mechanical | assem.murad@pyramakerz.com | Engineer | Junior
Eng. Mohaned | Ahmed Mohsen | Mechanical | ahmedmohsen4h4@gmail.com | Engineer | Junior
Eng. Seif |  | Embedded | eng.seif@pyramakerz.com | Senior | Senior
Eng. Seif | Eng. Asem Alroomy | Embedded | asem_h@outlook.com | Engineer | Junior
Eng. Rawan |  | Visual/Graphic | Rawan.Aleithy@pyramakerz.com | Senior | Senior
Eng. Nehal |  | Flutter | eng.nehal@pyramakerz.com | Senior | Senior
Eng. Maged |  | AI | eng.maged@pyramakerz.com | Senior | Senior
Eng. Mohaned | Haisam | Mechanical | haythamkhaledeng@gmail.com | Engineer | Junior
Eng. Rawan | Nouran | Visual/Graphic | Rawan.Aleithy@pyramakerz.com | Engineer | junior
Eng. Seif | Ahmed Mohsen | Embedded | ahmedmohsen4h4@gmail.com | Engineer | Junior

## Custom_Tasks
Task ID | Engineer Name | Task Type | Description | Date | Hours Spent | Status

## Tasks
Task_ID | Project_ID | Project_Name | Task_Name | Description | Department | Start_Date | End_Date | Status
| 1 | RC Car |  |  | Embedded
| 2 | Hydroponics |  |  | Mechanical
| 3 | Generic Kit |  |  | Mechanical

## Project_Timeline
Project_ID | Project_Name | Start_Date | End_Date | Progress | Notes

## Engineer History Viewer
Engineer Name | Report history for: Asem Alroomy
Asem Alroomy
No reports found.

## Access_Control
Name | Role | Department(s) | Access Level | Email
CTO | Executive | All | Full Access | cto@pyramakerz.com
Eng. Seif | Manager | All | Full Access | eng.seif@pyramakerz.com
Eng. Maged | Senior | AI | Team Access | eng.maged@pyramakerz.com
Eng. Mohaned | Senior | Mechanical | Team Access | eng.mohaned@pyramakerz.com
Eng. Rawan | Senior | Visual/Graphic | Team Access | eng.rawan@pyramakerz.com
Eng. Nehal | Senior | Flutter | Team Access | eng.nehal@pyramakerz.com
Eng. Asem Alroomy | Engineer | Embedded | Self Access | eng.asem@pyramakerz.com
Assem Murad | Engineer | Mechanical | Self Access | assem.murad@pyramakerz.com

## Analytics Dashboard
Department | Total Reports | Unique Members | Last Submission | Pending Members
No data available yet.

## Dashboard
📊 Daily Reporting Dashboard
|  | ✅ System Check Passed | 2025-10-17 17:07
Metric | Value
Total Reports (All) | 6
Embedded Reports | 0
AI Reports | 0
Mechanical Reports | 6

## Master_Log
LoggedAt | Engineer | Department | Project | TaskID | Feature | ShortDesc | DurationHours | Status

## Senior_Review
LoggedAt | Engineer | Department | Project | TaskID | Senior | ReviewDate | Comments | Approval

## Embedded_Reports
Timestamp | Date | Engineer | Department | Project | TaskID | Feature/Module | Description | Start Time | End Time | Git Ref | Status | Notes | Assigner | DurationHours

## AI_Reports
Timestamp | Date | Engineer | Department | Project | TaskID | Model/Task | Dataset/Module | Description | Start Time | End Time | Experiment/Git | Status | Notes | Assigner | DurationHours

## Mechanical_Reports
Timestamp | Date | Engineer | Department | Project | TaskID | Part/Assembly | Description | Start Time | End Time | CAD/Ref | Status | Notes | Assigner | DurationHours